## Sheet1
# | Reported Date [MM-DD-YYYY] | Reported By | Severity [P0-P5] | Status [open, in-progress, resolved, won't fix] | Assigned To | Short Desc. | Expected Results | Actual Results | Steps to reproduce
1 | 2025-02-19 | William | P2 | resolved | William | Smoke not despawning after a set time | Smoke particles should stop spawning after the SmokeBlock timer is <= 0 | Smoke particles continue spawning regardless of timer value | 1. Create a FireBlock 2. Wait for it to run out so that it starts spawning smoke particles 3. Observe that the smoke particles continue to spawn forever
2 | 2025-02-19 | Abhi | P2 | resolved | Abhi | FireBlock creation being triggered inconsistently while moving | Player should stop moving and FireBlocks should be placed as normal | Player stops moving and FireBlocks are sometimes not placed at all | 1. Press and hold a movement key 2. Press and release spacebar while moving towards an empty cell 3. Do not let go of the movement key 4. Observe that the FireBlock is not created until another keyboard event occurs
3 | 2025-02-19 | Simrit | P0 | resolved | Simrit | Placing and removing FireBlocks multiple times in succession leads to a game crash (likely related to particles) | Game should not crash when placing and removing FireBlocks multiple times in succession | Game crashes when placing and removing FireBlocks multiple times in succession | 1. Move player to an area with a lot of space in front of them (to place fire in) 2. Spam press the spacebar key for about 20 seconds 3. Observe that the game crashes with an OpenGL error "INVALID_VALUE"
4 | 2025-02-20 | Abhi | P2 | open | Abhi | Enemies occasionally snap to cells (faulty collision resolution) when FireBlocks are placed near them. This is due to the Grid-Entity map not accounting for Entities transitioning between grid cells | FireBlocks should not be allowed to be placed on cells partially occupied by Enemies | FireBlocks are allowed to be placed on cells partially occupied by Enemies, leading to Enemies snapping to other cells | 1. Move near an Enemy 2. Press spacebar to place fire towards the Enemy 3. Observe that while the Enemy transitions from cell to cell, it snaps to a nearby empty cell to resolve the collision with fire
5 | 2025-02-20 | Suha | P2 | open | Abhi | Enemies occasionally freeze or disappear when FireBlocks are placed near them, if they occupy the same cell as an ingredient. Related to collision resolution; Enemies are likely snapping off the playable grid. Likely related to the above bug | FireBlocks should not be allowed to be placed on cells occupied by Enemies | FireBlocks are allowed to be placed on cells occupied by Enemies, leading to strange interactions with Enemy-Fire collision resolution | 1. Wait for an Enemy to move towards an area with many obstacles 2. Move near the Enemy 3. Press spacebar to place fire as the Enemy moves onto a cell with an ingredient 4. Observe that the Enemy either gets stuck inside a FireBlock or disappears
6 | 2025-03-05 | Simrit | P0 | resolved | Abhi | If A* enemy (water) cannot find a path to the player the game crashes |  |  | 1. Create a box of fire around player such that there is no path for the enemy to get to the player
7 | 2025-03-07 | William | P4 | open | William | Smoke particles not despawning when switching levels | Should be no smoke particles spawned when switching levels | Smoke particles appearing when switching levels, smoke from previous level appearing in another level | 1. go to level 2, spawn fire in a line and delete fire so smoke particles start spawning 2. go to main menu and select level 3, there will be smoke particles that remained from level 2
8 | 2025-03-08 | Suha | P2 | open |  | when two enemies collide with eachother they tend to glitch in place as if they keep bumping into eachother until they find a proper new position | at an enemy-enemy collision there should be an automatic bounce in a different direction no glitch | both sprites keep bouncing into eachother | 1. you can use fire to get them in the same area. not always only sometimes
9 | 2025-03-09 | Suha | P2 | resolved | Wiliam | When you die from either time out or death restart closes the game | restart should restart the level | the game shuts down as if you have pressed 'esc' | 1. Die to an enemy such that the popup screen appears and click "RESTART"